## Read Me
Project Odyssey - MVP Backlog
Working tracker for developers. The source of truth is Project Odyssey.docx v2.0, chapter 12; this workbook is generated from the same data. Updated 2026-10-01: M7-M9 added (D-34); statuses of built stories set to Done.
How to use
1. Work milestone by milestone (Timeline sheet). Never start a story whose dependencies are not Decided (Dependencies sheet).
2. Update only the yellow cells: Status on the User Stories sheet, the project start date and week estimates on the Timeline sheet.
3. Status values: To do, In progress, Blocked, Done. A story is Done only when it meets the Definition of Done.
4. Epic progress and the timeline recalculate automatically.
5. Example: set US-001 to 'In progress' when you start installing tools, and to 'Done' when a clean checkout builds and debugs.
Story sizes (used by formulas)
Size | Weeks (low) | Weeks (high) | Meaning (part-time, beginner pace, learning included)
S | 0.5 | 1 | Up to about a week
M | 1 | 2 | One to two weeks
L | 2 | 4 | Two to four weeks; split if it grows

## MVP Definition
MVP definition
Product Owner + Solution Architect, 2026-09-29. Status 'Proposed' = awaiting your decision.
Hypothesis
We believe that living one Neanderthal's life on a procedurally generated region, from the Growing Period to leading a clan, will produce emergent stories that make players want to keep playing. We will know when at least 5 of 8 outside playtesters play 30+ minutes unprompted and at least 3 can retell a story that emerged from the simulation. At the same time, the MVP proves the architecture: 60 FPS, deterministic, headless-testable, on Windows x64.
Scope (in)
ID | Area | MVP scope | Status | Traces to
MVP-01 | Platform | Windows x64 only. Android and iOS are out of the MVP (architecture keeps them possible). | Proposed | PLT-01, PLT-02
MVP-02 | Age | Age 1 only: Late Paleolithic, Age of Embers (c. 40,000 BCE). | Proposed | ENV-01, ENV-09
MVP-03 | World | One procedurally generated region (256 x 256 tiles, 64 x 64-tile chunks), not a whole planet. Bounded edges; planet projection deferred. | Proposed | ENV-03, ARC-06, OPEN-02
MVP-04 | Game Mode | One Hero per Age only (smallest scope, recommended first mode). | Proposed | CHR-02
MVP-05 | Modifiers | Only the baseline modifier Random per World, plus Growing Period presets (Off / Compressed / Full) and the Comfort dial (Cozy / Balanced / Harsh). | Proposed | CHR-03, CHR-06, ENV-07
MVP-06 | Character | Full Growing Period (ages 12-26) with Focus slots, Crossroads events, imprint curve and the Mantle moment; aging and death. | Proposed | CHR-05, CHR-06
MVP-07 | Professions | Five Age 1 professions, data-driven: Hunter, Gatherer, Flint-knapper, Fire-keeper, Shaman-healer. | Proposed | CHR-07, Flag 5
MVP-08 | Pillars | Two pillars playable at region scale: Trade (barter and debts) and Religion (sacred fire and followers). The other four are shown as locked 'later Ages'. | Proposed | PIL-02, PIL-04, ENV-10
MVP-09 | Victory | Win: your clan leads the region (Dominion 60% in Trade or Religion, or 50% combined). Lose: your hero dies before the Mantle moment, or your clan disbands. | Proposed | ENV-05, ENV-10
MVP-10 | Simulation | One player clan (about 20 people) and two rival AI clans; LOD tiers Active and Nearby only. | Proposed | ARC-05, ADR-013
MVP-11 | Presentation | Layered 32 x 48 sprites with 3 outfits per body; programmer or placeholder art allowed; minimal sound effects. | Proposed | ENV-11, ENV-12, OPEN-11, OPEN-12
MVP-12 | Time model | Pausable real time with speed control (pause, 1x, 2x, 4x). Decided by the owner (D-01, 2026-09-30). | Decided | ADR-006, OPEN-04
MVP-13 | Physics | Luna Physics core: deterministic 3D fixed-point math, hit detection, ballistics, basic rigid bodies and material properties, proven by a spear throw in the demo (M1b). Advanced physics and chemistry return with later Ages. | Decided | PHY-01..PHY-06, ARC-10, ADR-017
MVP-14 | Interactions | Data-driven world interactions shared by the player, NPCs and animals; talking to NPCs (written + generated); interactions and dialogue editable offline (JSON, .dlg) and in the Editor's graph view. Built before kill gate 2 (D-34, 2026-10-01). | Decided | INT-01..INT-06, SDC-03..SDC-06, ADR-019
Success and kill criteria (decided before building)
Metric | Target | How measured | Gate
Voluntary play time | 5 of 8 playtesters play 30+ minutes without being asked to continue | Observation + local session log (US-092) | M6
Emergent story | 3 of 8 can retell a story that came from the simulation, not from a script | Post-play interview | M6
Chronicle interest (early) | 2 of 3 readers find a story in the console chronicle | Show printed chronicle (M2: 3 readers, failed 2026-09-30; M2b retry: the owner reads and judges) | M2, retried at M2b
Frame rate | 60 FPS with 500 simulated agents in the region on the minimum PC (OPEN-19) | FPS overlay (US-082) | M5
Determinism | Same seed + inputs give the same world hash after 10,000 ticks | Automated test in CI | M2 onwards
Stability | No crash in a 2-hour play session or a 100-year soak test | Soak test + crash log | M5, M6
Kill / pivot rule | If M2 or M6 fails: stop adding content; redesign the simulation or the loop first | Owner decision, recorded | M2, M6

## Timeline
Timeline: milestones and Gantt (likely plan)
Estimates are bottom-up from story sizes, part-time, beginner pace. Yellow cells are editable. Bars show the likely plan.
Project start (Monday) | 2026-10-05
ID | Milestone | Learning stages | Weeks optimistic | Weeks pessimistic | Weeks likely | Start week | End week (likely) | Start date | End date (likely) | End date (optimistic) | End date (pessimistic) | Must story weeks (low-high) | Exit criteria (demonstrable) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140
M0 | Tooling ready | 0 | 2 | 4 |  | 1 | [6 empty] | A clean checkout builds in Visual Studio; you pause the program on a breakpoint; CI runs on push.
M1 | Luna engine: walking skeleton | 3-4 | 5 | 9 | [8 empty] | Luna opens a window; a demo character walks around a tile map at 60 FPS with crisp pixels at any window size; the build proves Luna contains no Odysseus code.
M1b | Luna Physics (deterministic 3D) | 5 | 6 | 12 | [8 empty] | Luna Physics passes its math, hit-detection, ballistics and rigid-body tests identically on every build; in the demo the hero throws a spear that flies in an arc with a shadow and hits a target.
M2 | Console clan simulator (KILL GATE 1) | 1-2 | 8 | 15 | [8 empty] | The headless runner simulates a 20-person clan for 100 years without crashing; the printed chronicle is shown to 3 people and at least 2 find a story in it; the determinism test passes.
M2b | Story engine (KILL GATE 1 retry) | 1-2 | 10 | 20 | [8 empty] | The chronicle tells the clan's story in fewer, bigger episodes with reasons; every death and feud says why; the 100-year soak still runs without crashing and the determinism test passes; the owner reads the printed story and judges whether it is a story (Kill Gate 1 retry).
M2c | Level editor (Game mode and Editor mode) | 1-2 | 3 | 8 | [8 empty] | The owner switches between Game mode and Editor mode, paints ground tiles, places characters with properties, sets the level's name, size, default ground and hero start, saves, reloads and plays the level; the demos still work.
M2d | Content and combat (weapons, nature, effects, weather) | 2026-01-02 | 4 | 9 | [8 empty] | The hero fights with 16 starter weapons of 8 classes and elements; enemies strike back; plants block, are chopped and eaten and regrow; animals and effects are placed in the Editor; the weather changes by itself.
M3 | Living clan on screen | 5-6 | 3 | 6 | [8 empty] | The clan from M2 and M2b runs inside the game; NPCs are visible, dressed in layered outfits, and act on their needs.
M4 | Region, tools and saves | 7-9 | 5 | 10 | [8 empty] | A region is generated from a seed with biomes, resources and two rival clans; any NPC can be inspected; the game saves and loads.
M5 | Vertical slice feature-complete | 10 | 16 | 31 | [8 empty] | A player can start a new game, live the Growing Period, take a profession, pursue Trade or Religion, and win or lose.
M7 | World interactions | - | 8 | 16 | [8 empty] | Every action in today's game comes from data files; the player, NPCs and animals act on things with timed, visible, saved results; files edited offline reload with F5 and errors name file and line.
M8 | Speak to NPCs | - | 7 | 14 | [8 empty] | The player talks to any clan member; written conversations branch on the simulation; without a script NPCs make small talk from their memories; talk changes opinions, items and memories; NPCs talk to each other in bubbles.
M9 | Interaction and dialogue editor | - | 8 | 16 | [8 empty] | The owner opens any dialogue or interaction in the Editor as a graph, edits it, test-plays it and saves it, and the file still reads well in a text editor.
M6 | Playtest and go/no-go (KILL GATE 2) | - | 3 | 4 | [8 empty] | 8 outside playtesters play; success criteria measured; go/no-go decision recorded. Held after M9 (owner, 2026-10-01, D-34).
| MVP total | [11 empty] | Months (likely) = weeks / 4.33
In months
Why the estimate grew: the learning path (requirements, section 8.3) estimated 9-13 months top-down. The bottom-up sum of the MVP stories is higher; this sheet uses the bottom-up figure.
Buffer: the 'Should' stories are the cut list if time runs short. Cutting all of them saves about 5-11 weeks.
Kill gates: M2 (is the console chronicle interesting? failed 2026-09-30, passed at the M2b retry) and M6 (do playtesters stay?), held after M9 (D-34). Critical path: M0 > M1 > M1b > M2 > M2b > M2c > M2d > M3 > M4 > M5 > M7 > M8 > M9 > M6. Dates of M2c onwards are not re-planned yet.

## Dependencies
Dependencies
Design decisions you owe, external needs, and the technical chain. A story is Ready only when its dependencies are Decided.
ID | Dependency | Type | Needed by | Blocks | Owner | Status
D-01 | Confirm time model: pausable real time with speed control (OPEN-04) | Design decision | M2 | US-010 | Owner | Decided
D-02 | Side Characters: needs, traits, relationships (OPEN-10). Decided by Dominus (delegated), 2026-09-30. | Design decision | M2 (week 3) | US-011, US-012, US-013 | Owner + Dominus | Decided
D-03 | Confirm the Age 1 needs set: Hunger, Energy, Warmth, Social | Design decision | M2 | US-011 | Owner | Decided
D-04 | Sprite size and facing directions (OPEN-11). Owner answer 2026-09-29: 32x48 px, 8 directions. | Design decision | M1 | US-022, US-024, US-030 | Owner | Decided
D-05 | Art source for placeholders: own, free asset pack, or hired (OPEN-12) | Design decision | M3 | US-030 | Owner | Decided (2026-09-30): own art, placeholder quality; licence checked before a public release
D-06 | Minimum PC spec (OPEN-19) | Design decision | M4 | US-082 | Owner | Open
D-07 | Calendar display (OPEN-15) | Design decision | M4 | US-050, US-083 | Owner | Open
D-08 | Interactions interview: verbs, objects, crafting (OPEN-09) | Design decision | M4 | US-061, US-062 | Owner + Dominus | Decided (answered by D-34)
D-09 | Confirm the five Age 1 professions (MVP-07) | Design decision | M4 | US-060 | Owner | Proposed
D-10 | Confirm MVP pillars Trade + Religion (MVP-08) and victory thresholds (MVP-09) | Design decision | M5 | US-070..US-073 | Owner | Proposed
D-11 | Story interview: tone of events, onboarding elder (OPEN-08) | Design decision | M5 | US-052, US-090 | Owner + Dominus | Open
D-12 | Visual Studio, CMake, Git, vcpkg installed; GitHub account and private repo | External / tooling | M0 | US-001, US-002 | Owner | Decided
D-13 | SDL3, EnTT, Dear ImGui, nlohmann/json, doctest, FastNoiseLite available via vcpkg or third_party | External / libraries | M0-M4 | US-020, US-032, US-083, US-016, US-040 | Developer | Decided
D-14 | Eight outside playtesters recruited | External / people | M6 | Kill gate 2 | Owner | Open
D-15 | Technical chain: M0 > M1 > M1b > M2 > M2b > M2c > M2d > M3 > M4 > M5 > M7 > M8 > M9 > M6 (each milestone needs the previous one) | Technical | All | All | Developer | Planned
D-GATE-M2 | Kill Gate 1 result: did 2 of 3 readers find a story in the console chronicle? | External / people | M2 exit | M3 (all) | Owner | Decided: Pivot
D-18 | Story pivot design: story arcs on a richer social simulation; quarrels, blame, revenge; sharing and nursing; courtship and rivals; teaching and hunting parties; episodes plus lines with reasons; the owner judges the retry alone | Design decision | M2b | US-110..US-115 | Owner | Decided
D-GATE-M2b | Kill Gate 1 retry: the owner reads the M2b story and judges whether it is a story | External / people | M2b exit | M3 (all) | Owner | Decided: Go (2026-09-30)
D-19 | Level editor scope v1: settings are level and character properties; placed characters stand still with properties; new milestone M2c before M3 | Design decision | M2c | US-120..US-126 | Owner | Decided
D-21 | M2d content and combat: full gameplay; 16 starter weapons as pickups with a 9-slot hotbar; 8 weapon classes; elements; hero 100 HP; enemies strike back within 1.5 m after 0.5 s; plants block, chop, heal 10, regrow in 15 s in camera view; predators and boars are enemies; effects; random weather every 60-120 s | Design decision | M2d | US-130..US-138 | Owner | Decided
D-22 | Design decisions are taken by the owner in interactive question rounds in chat; Dominus no longer delegates design or scope questions | Process decision | all | all | Owner | Decided
D-34 | World interactions and dialogue (Round 13): plain-text .dlg dialogue + JSON interactions (comments allowed); hybrid talk (written trees reading the simulation + generated small talk); full visual graph editor plus F5 hot reload; build M7-M9 first, kill gate 2 after | Design decision | M7 | US-150..US-175 | Owner | Decided

## Epics
Epics
Counts, effort and progress are formulas over the User Stories sheet.
ID | Epic | Outcome | Milestone | Stories | Must | Weeks (low) | Weeks (high) | Done | Progress
E0 | Foundations | Every change builds, is tested and is safe to make. | M0
E1 | Headless clan simulation | A clan lives, remembers and produces a readable chronicle, with no graphics. | M2
E2 | Luna engine walking skeleton | The player sees and controls a character in a window. | M1
E3 | Characters on screen | The simulated clan is visible and readable at a glance. | M3
E4 | Procedural region | Every new game has a different, believable region to live in. | M4
E5 | Life and the Growing Period | The player's choices from 12 to 26 shape who the hero becomes. | M5
E6 | Professions and interactions | The player works, crafts and learns a trade in the world. | M5
E7 | Pillars and regional dominion | The player can lead the region through Trade or Religion. | M5
E8 | Saves, settings and quality | The game is stable, fast, and never loses progress. | M4-M5
E9 | Playtest readiness | Outside players can install, learn and play the slice. | M6
E10 | Luna physics | Luna simulates hits, throws and bodies with deterministic 3D physics. | M1b
E11 | Story engine | The clan's life becomes a readable story: episodes with causes, people and consequences. | M2b
E12 | Level editor | The owner builds levels by hand (ground tiles, characters and settings) and plays them at once. | M2c
E13 | Content and combat | The owner's weapons, plants, animals, effects and weather are in the game and playable. | M2d
E14 | World interactions | Every thing in the world offers actions from data; the player, NPCs and animals act on things with timed, visible, saved results. | M7
E15 | Speak to NPCs | The player talks to any clan member; written and generated conversations read the simulation and change it; NPCs talk to each other. | M8
E16 | Interaction and dialogue editor | The owner edits every conversation and interaction as a graph in the Editor, test-plays it and saves readable files. | M9
Total

## User Stories
User stories with acceptance criteria
Yellow Status column is yours. Weeks come from the size table on Read Me. Gherkin: Given (context), When (action), Then (observable result).
ID | Epic | Title | User story | Acceptance criteria | Priority | Size | Weeks (low) | Weeks (high) | Milestone | Depends on | Traces to | C++ you will learn | Notes | Status
US-001 | E0 | Build and debug from a clean checkout | As a developer, I want to clone the repository and build every target with one CMake preset, so that I can start working in minutes and never fight the build. | Scenario: Clean build Given a fresh clone and the installed toolchain When I run the windows-x64-debug preset and build Then odysseus.exe, odysseus_headless.exe and odysseus_tests.exe are produced with zero warnings Scenario: Debugging Given the Debug build When I set a breakpoint in main() and start debugging in Visual Studio Then execution pauses at the breakpoint and I can inspect variables Scenario: Missing dependency Given a library missing from vcpkg.json When I build Then CMake fails with a message naming the missing library | Must | S |  |  | M0 | D-12 | ADR-001, ADR-012, TEC-04 | What compiler, linker and build system each do; CMake presets |  | Done
US-002 | E0 | Run the build and tests on every push | As a developer, I want GitHub Actions to build and test every push on a Windows runner, so that mistakes are caught automatically, even when I forget to run tests. | Scenario: Green push Given a commit that builds and passes tests When I push to GitHub Then the CI run succeeds within 15 minutes Scenario: Broken test Given a commit with a failing test When I push Then the CI run fails and names the failing test | Must | S |  |  | M0 | US-001, D-12 | ADR-014 | Git basics: commit, branch, push |  | Done
US-003 | E0 | Enforce the layer rules in the build | As a developer, I want the build to reject code that breaks the five-layer rule or pulls game code into Luna, so that the architecture cannot rot by accident. | Scenario: Allowed use Given Game code that includes an Engine header When I build Then the build succeeds Scenario: Forbidden use Given Simulation code that includes an Engine or SDL3 header When I build Then the build fails with an include error Scenario: Luna stays game-agnostic Given Luna code that includes a Simulation or Game header When I build Then the build fails with an include error | Must | S |  |  | M0 | US-001 | ARC-01, ARC-02, ARC-09, ADR-004 | CMake targets and target_link_libraries |  | Done
US-004 | E0 | Log what happens and stop on broken assumptions | As a developer, I want a logging system and asserts in Core, so that I can see what the game did before a problem. | Scenario: Log file Given the game has run When I open the per-user logs folder Then a log file for the session exists with timestamped lines Scenario: Rotation Given six sessions have run When I open the logs folder Then only the last five session logs are kept Scenario: Assert Given a Debug build and an assert whose condition is false When that line runs Then the debugger stops there and the log records file and line | Must | S |  |  | M0 | US-001 | Architecture 7.8 | Header/source files, namespaces, macros |  | Done
US-010 | E1 | Advance a seeded world clock | As a developer, I want the simulation to tick 20 times per second of game time with a calendar of days and seasons, so that everything in the world happens on one reliable clock. | Scenario: Calendar Given a new simulation with seed 42 When it runs for one in-game year Then the calendar has passed through four seasons and the day counter matches the configured year length Scenario: Determinism Given two runs with seed 42 and the same inputs When each runs 10,000 ticks Then both produce the same world hash Scenario: Speed control Given the simulation at speed 4x When one real second passes Then 4 seconds of game time have advanced | Must | M |  |  | M2 | D-01 | ADR-006, ADR-011, ARC-07, MVP-12 | The game loop and accumulator; integers vs floats |  | Done
US-011 | E1 | Give every person needs that change over time | As a player, I want clan members to get hungry, tired, cold and lonely, so that the world feels alive and people have reasons to act. | Scenario: Decay Given a person with full needs When one in-game day passes without eating, sleeping, warmth or company Then each need has dropped by its configured daily rate Scenario: Satisfaction Given a hungry person When they eat a meal Then Hunger rises by the meal's value, capped at the maximum Scenario: Consequence Given a person whose Hunger stays at zero for the configured number of days When the next day starts Then they die and the chronicle records the cause | Must | M |  |  | M2 | D-02, D-03 | SDC-01 (candidate), Overview v0.1 | Plain structs as components; std::vector | Needs set is an assumption until D-03 is confirmed. | Done
US-012 | E1 | Let people choose what to do (utility AI) | As a player, I want each clan member to pick sensible actions based on their needs and skills, so that the clan survives without me micromanaging it. | Scenario: Pick best action Given a person who is very hungry and slightly tired When the AI evaluates available actions Then a food action (gather or hunt) scores highest and is chosen Scenario: No option Given a person with no reachable action that satisfies a need When the AI evaluates Then they wander or rest instead of freezing, and no error occurs Scenario: Inspectable Given any person When I print their last decision in the headless runner Then I see every action's score and the chosen one | Must | L |  |  | M2 | US-011, D-02 | SDC-01 (candidate utility AI) | Functions as systems; enums; sorting |  | Done
US-013 | E1 | Remember events and spread gossip | As a player, I want people to remember important events and tell others, so that reputations form and stories travel through the clan. | Scenario: Memory Given a person who is given a gift When the event happens Then they store a memory with who, what, when and a feeling Scenario: Gossip Given two people who talk When one has a memory the other lacks Then the listener may gain a slightly weaker copy of that memory Scenario: Forgetting Given a minor memory older than its lifetime When the day ends Then it is forgotten; important memories are kept | Must | M |  |  | M2 | US-012, D-02 | GD-03 (candidate), SDC-01 | Containers of structs; references |  | Done
US-014 | E1 | Write a readable chronicle | As a player, I want notable events recorded as short sentences, so that I can read the clan's story and share it. | Scenario: Record Given a birth, death, first hunt of a mammoth or a feud When it happens Then the chronicle adds one sentence with the in-game date, e.g. 'Spring, year 3: Ura was born to Tok and Maa.' Scenario: Filter Given hundreds of minor events in a year When I print the chronicle for that year Then only events above the importance threshold appear | Must | M |  |  | M2 | US-013 | NA-02 (candidate tapestry) | std::string and formatting |  | Done
US-015 | E1 | Soak-test the simulation from the command line | As a developer, I want to run the headless simulation for N years with a seed and get a report, so that I can check stability and balance in seconds. | Scenario: Run Given the command odysseus_headless --seed 7 --years 100 When it runs Then it finishes without crashing and prints population, deaths by cause, average needs and tick time Scenario: Bad input Given --years -5 When I run it Then it prints a usage message and exits with an error code | Must | S |  |  | M2 | US-010..US-014 | AQ-01, NFR-03, NFR-04 | main(), command-line arguments |  | Done
US-016 | E1 | Save and load the simulation | As a player, I want to save the world and load it later exactly as it was, so that I never lose my progress. | Scenario: Round trip Given a simulation after 50 years When I save and load it Then the world hash after loading equals the hash before saving Scenario: Crash-safe Given a save interrupted halfway When I load Then the previous complete save loads and nothing crashes Scenario: Old version Given a save file from an earlier save version When I load it Then it is upgraded and loads, or a clear message explains why it cannot | Must | M |  |  | M2 | US-010, D-13 | ADR-010, NFR-05 | File I/O, JSON, error handling |  | Done
US-020 | E2 | Open a window with a steady game loop | As a player, I want the game to open a window that runs smoothly and closes cleanly, so that the game feels solid from the first second. | Scenario: Open Given the game is started When it launches Then a 1280 x 720 window opens within 3 seconds Scenario: Steady Given the loop is running When the frame time is measured for 60 seconds Then the average is 60 FPS on the development PC and simulation speed is identical at 30 and 144 Hz monitors Scenario: Close Given the window is open When I press the close button Then the game shuts down with no error in the log | Must | M |  |  | M1 | US-001, D-13 | ADR-002, ADR-006, TEC-05 | RAII wrapper around SDL_Window; unique_ptr with a custom deleter |  | Done
US-021 | E2 | Control the game through intents | As a player, I want keyboard, mouse and gamepad to control the same actions, so that I can play the way I like, and touch can be added later. | Scenario: Keyboard Given the default bindings When I press W Then the Move Up intent is produced Scenario: Gamepad Given a connected gamepad When I push the left stick up Then the same Move Up intent is produced Scenario: No raw keys Given the Game layer code When it is reviewed Then it only reads intents, never key codes | Must | S |  |  | M1 | US-020 | ARC-03 | Enums, mapping tables, std::unordered_map |  | Done
US-022 | E2 | Draw sprites with crisp pixels | As a player, I want pixel art to stay sharp at every window size, so that the game looks right on any screen. | Scenario: Integer scaling Given a 480 x 270 virtual screen When the window is resized to 1920 x 1080 Then the image scales by exactly 4 with no blurred pixels Scenario: Odd size Given a window size that is not an exact multiple When it is resized Then the image uses the largest whole-number scale and letterboxes the rest | Must | M |  |  | M1 | US-020, D-04 | ENV-11, ADR-003 | Interfaces with virtual functions (Renderer) |  | Done
US-023 | E2 | Show a tile map with a following camera | As a player, I want to see the world around my character, with the camera following me, so that I always know where I am. | Scenario: Draw Given a 64 x 64 test map When the game runs Then tiles within the camera view are drawn and tiles outside are skipped Scenario: Follow Given the character near the map centre When it moves Then the camera follows smoothly and stops at the map edges | Must | M |  |  | M1 | US-022 | Architecture 7.4 | 2D grids stored in a 1D vector |  | Done
US-024 | E2 | Walk the character around the map | As a player, I want to move my character in four directions with animation, so that I feel in control of a person in the world. | Scenario: Walk Given the character is idle When I hold Move Right Then it walks right with a walking animation at the configured speed Scenario: Blocked Given a rock tile to the right When I walk into it Then the character stops at the tile edge Scenario: Idle Given the character is walking When I release all movement input Then it stops and plays the idle animation facing the last direction | Must | M |  |  | M1 | US-021, US-023, D-04 | ENV-11 | State machines; simple collision |  | Done
US-030 | E3 | Compose characters from layers | As a player, I want characters built from body, hair, outfit and held-item layers with colour variants, so that every person looks different and outfits can grow with progression. | Scenario: Compose Given a body, a hair style, an outfit and a spear When the character is drawn Then all four layers line up in every animation frame and direction Scenario: Swap Given a character wearing outfit A When the outfit changes to B Then only the outfit layer changes Scenario: Palette Given one hair sprite When three palettes are applied Then three distinct hair colours appear without new art | Must | M |  |  | M3 | US-024, D-04, D-05 | ENV-12, MVP-11 | Composition over inheritance |  | Done
US-031 | E3 | Read people's state at a glance | As a player, I want to see how people feel from their posture and small emote icons, so that I understand the clan without opening menus. | Scenario: Emote Given a person whose Warmth is critical When they are on screen Then a shiver animation or cold emote is visible Scenario: Details on demand Given any person When I hover or click them Then a panel shows exact need values and current action | Should | S |  |  | M3 | US-032, US-011 | UX-01 (candidate) | Mapping data to presentation |  | Done
US-032 | E3 | See the simulated clan on screen | As a player, I want clan members from the simulation to appear and act in the world, so that I watch the clan live its life. | Scenario: Mirror Given 20 people in the simulation When the game renders Then 20 characters appear at their simulated positions Scenario: Smooth Given the simulation ticking at 20 Hz When characters move Then their movement is interpolated and looks smooth at 60 FPS Scenario: Separation Given the Simulation layer When the build is checked Then it contains no rendering code (US-003 still passes) | Must | L |  |  | M3 | US-012, US-024 | ADR-004, ADR-005, ARC-05 | EnTT registry and views; interpolation |  | Done
US-040 | E4 | Generate a region from a seed | As a player, I want each new game to create a different region with steppe, forest, river and caves, so that every playthrough feels new. | Scenario: Variety Given seeds 1 and 2 When regions are generated Then they differ in layout and biome placement Scenario: Repeatable Given seed 1 twice When regions are generated Then they are identical tile for tile Scenario: Playable Given any seed When a region is generated Then the start area is reachable, has water and food within 20 tiles, and generation takes under 10 seconds | Must | L |  |  | M4 | US-023, D-13 | ENV-03, ARC-06, ADR-009, MVP-03 | Noise functions; seeded random numbers |  | Done
US-041 | E4 | Place resources by biome | As a player, I want flint, wood, berries and animals placed where they make sense, so that exploring the land matters. | Scenario: Biome rules Given a generated region When resources are placed Then flint appears near rivers and caves, berries in forest edges, herds on the steppe Scenario: Regrowth Given a berry bush that was harvested When the configured days pass in the right season Then it regrows | Must | M |  |  | M4 | US-040 | Overview v0.1 (materials) | Data tables from JSON |  | Done
US-042 | E4 | Spawn rival clans | As a player, I want two AI clans living elsewhere in the region, so that there are others to trade with, convert, or compete against. | Scenario: Spawn Given a new region When the game starts Then two rival clans of 10-20 people exist at least 60 tiles from the player's camp Scenario: Autonomy Given rival clans When a year passes Then they gather, move camp and grow or shrink on their own Scenario: LOD Given a rival clan far from the player When it is simulated Then it runs at the Nearby tier rate (1 tick/s) | Must | M |  |  | M4 | US-040, US-012 | ARC-05, MVP-10 | Reusing systems for different data |  | Done
US-043 | E4 | Stream chunks and save only changes | As a developer, I want the region stored as a seed plus changed chunks, so that saves stay small and loading is fast. | Scenario: Streaming Given the player walking across the region When they approach unloaded chunks Then chunks load before they become visible with no stutter over 50 ms Scenario: Delta save Given a region where 3 chunks were changed When the game is saved Then only those 3 chunks are stored besides the seed | Should | M |  |  | M4 | US-040, US-016 | ARC-06, ADR-009 | Hashing chunk coordinates |  | Done
US-050 | E5 | Start a new game | As a player, I want to choose a seed, a Growing Period preset and a Comfort level before starting, so that I can shape the kind of game I want. | Scenario: Defaults Given the New Game screen When I press Start without changing anything Then a random seed, Full Growing Period and Balanced comfort are used, and my hero starts at age 12 Scenario: Seed Given I type seed 1234 When I start two games with it Then both regions and heroes are identical Scenario: Preset Off Given Growing Period set to Off When I start Then the hero starts at 26 with affinities generated from the origin | Must | M |  |  | M5 | US-040, D-07 | CHR-03, CHR-06, ENV-07, MVP-05 | UI state and screens |  | Done
US-051 | E5 | Choose how to spend each year of youth | As a player, I want to pick Focus activities each in-game year, so that I decide what kind of person my hero becomes. | Scenario: Choose Given a new year in the Growing Period When the Focus screen opens Then I can choose 2 activities (e.g. Hunt with elders, Tend the fire, Wander) Scenario: Effect Given I chose Tend the fire When the year ends Then Fire-keeping skill and Religion affinity increase by base x imprint multiplier | Must | M |  |  | M5 | US-050, US-053 | CHR-05, Growing Period sheet | Data-driven choices |  | Done
US-052 | E5 | Face Crossroads events | As a player, I want story decisions with lasting consequences during youth, so that my choices feel meaningful. | Scenario: Trigger Given the Growing Period in progress When a year passes Then one Crossroads event appears, chosen from those whose conditions match Scenario: Consequence Given I choose an option When the event resolves Then its effects apply (affinity, relationship, trait) and the chronicle records it Scenario: Content Given the MVP data files When they are counted Then there are at least 10 Crossroads events, each with 2-3 options | Must | L |  |  | M5 | US-051, D-11 | CHR-05, NA-03 (candidate) | Loading and validating content from JSON |  | Done
US-053 | E5 | Weight choices by age (imprint curve) | As a developer, I want Path Affinity gains multiplied by the imprint curve, so that early choices shape the hero most, as designed. | Scenario: Curve Given default tunables When a decision is made at 12, 19 and 26 Then the multipliers are 3.00, 1.75 and 0.50 Scenario: After 26 Given an adult hero When a decision is made Then the settled multiplier 0.25 applies Scenario: Tunable Given a designer changes the peak to 4.0 in the data file When the game restarts Then the new curve is used with no C++ change | Must | S |  |  | M5 | US-050 | CHR-05, CHR-06, ARC-08 | Pure functions and unit tests |  | Done
US-054 | E5 | Reveal the specialty at the Mantle moment | As a player, I want my hero's specialty revealed at 26, so that I see the result of my youth. | Scenario: Reveal Given the hero turns 26 When the Mantle event runs Then the top one or two affinities become the Specialty, shown on a summary screen and in the chronicle Scenario: Tie Given two affinities equal at the top When the Mantle event runs Then both become the Specialty | Must | S |  |  | M5 | US-053 | CHR-04, CHR-05 | Sorting and ties |  | Done
US-055 | E5 | Age, die, and end the run | As a player, I want my hero to age and eventually die, ending the run with a summary, so that every life has an arc and an ending. | Scenario: Aging Given a hero at 40 When years pass Then age affects energy decay by the configured amount Scenario: Death Given the hero dies When the death is processed Then the run ends with a summary: life events from the chronicle, specialty, and Dominion reached Scenario: Early death Given the hero dies before 26 When the run ends Then it counts as a loss (MVP-09) | Must | M |  |  | M5 | US-054, US-070 | CHR-02 (One Hero per Age), MVP-04, MVP-09 | Game states |  | Done
US-060 | E6 | Define the five Age 1 professions as data | As a designer (data editor), I want professions defined in JSON: skills, tools, actions, related pillar, so that content can grow without code changes. | Scenario: Load Given professions.json with Hunter, Gatherer, Flint-knapper, Fire-keeper, Shaman-healer When the game starts Then all five appear in-game Scenario: Validation Given a profession referencing a missing tool When the game starts Then a clear error names the file, the profession and the missing tool | Must | S |  |  | M5 | US-016, D-09 | CHR-07, ARC-08, MVP-07 | JSON parsing into structs |  | Done
US-061 | E6 | Interact with things through a context menu | As a player, I want to click a thing and pick from the actions it offers, so that I can do many things with everything in the world. | Scenario: Offer Given a berry bush and a player with empty hands When I click the bush Then a radial menu offers Gather and Inspect Scenario: Tool-gated Given a flint nodule and no hammerstone When I click it Then Knap is shown but disabled with the reason 'Needs a hammerstone' Scenario: Perform Given I choose Gather When the action completes Then the item enters my inventory and the bush shows as harvested | Must | L |  |  | M5 | US-024, D-08 | INT-01, GD-04 (candidate properties + verbs), UX-02 | Querying components; the Command pattern |  | Done
US-062 | E6 | Craft at a workstation | As a player, I want to turn materials into tools at a knapping stone or fire, so that my work produces useful things. | Scenario: Craft Given 2 flint and a hammerstone at a knapping stone When I craft a spearhead Then the flint is consumed and a spearhead is created Scenario: Quality Given Flint-knapping skill 1 vs 5 When each crafts a spearhead Then the higher skill gives a higher quality tier more often Scenario: Provenance Given a crafted item When I inspect it Then it shows who made it, from what, and when | Must | M |  |  | M5 | US-061, US-060 | GD-02 (candidate provenance) | Recipes as data |  | Done
US-063 | E6 | Learn a trade from a master | As a player, I want to apprentice with an NPC master once they trust me, so that skills and relationships grow together. | Scenario: Gated Given a master whose relationship with me is below the threshold When I ask to apprentice Then they refuse and say why Scenario: Learn Given an accepted apprenticeship When I work beside the master Then my skill in that profession grows faster than alone Scenario: Skill use Given any skill When I use it successfully Then it gains experience | Should | M |  |  | M5 | US-013, US-060 | CHR-07, SDC-01 (candidate) | Relationships as data |  | Done
US-070 | E7 | Track regional dominion | As a player, I want a Dominion Meter showing my clan's share of the region in Trade and Religion, so that I know how close I am to leading the region. | Scenario: Display Given the Dominion panel When I open it Then Trade and Religion show percentages; Military, Politics, Technology and Ideology show 'later Ages' Scenario: Update Given a trade or conversion happens When the day ends Then the relevant percentage updates | Must | M |  |  | M5 | US-042 | ENV-10, MVP-08 | Aggregating data across entities |  | Done
US-071 | E7 | Barter with rival clans | As a player, I want to exchange goods with other clans and track debts, so that Trade becomes a path to leadership. | Scenario: Barter Given my clan has 10 furs and a rival values furs When I offer 5 furs for 3 flint tools Then the rival accepts or counters based on its needs Scenario: Debt Given a rival accepts goods now for payment later When the deal closes Then a debt is recorded and counts toward my Trade dominion Scenario: Default Given a debt past its due date When the day ends Then the rival's relationship and my Trade dominion react as configured | Must | L |  |  | M5 | US-070, US-042 | PIL-02, MVP-08 | Integer arithmetic for goods (no floats) |  | Done
US-072 | E7 | Found a sacred fire and gather followers | As a player, I want to found a named sacred fire and hold rituals that attract followers, so that Religion becomes a path to leadership. | Scenario: Found Given Shaman-healer specialty or Fire-keeping skill 3+ When I found a sacred fire and name it Then it appears on the map with my custom name Scenario: Ritual Given a sacred fire When I hold a ritual with 5+ attendees Then attendees' faith grows and some rivals may convert over time Scenario: Neglect Given a sacred fire untended for the configured days When time passes Then it goes out and followers lose faith | Must | L |  |  | M5 | US-070, US-060 | PIL-04, MVP-08 | Events and timers |  | Done
US-073 | E7 | Win by leading the region | As a player, I want to win when my clan dominates the region, so that the run has a satisfying goal. | Scenario: Win Given Trade or Religion dominion reaches 60%, or combined reaches 50% When the day ends Then a victory screen shows the chronicle highlights and my specialty Scenario: Lose Given my clan drops below 3 members When the day ends Then the run ends as a loss with a summary | Must | S |  |  | M5 | US-070, US-071, US-072, D-10 | ENV-05, MVP-09 | Game-over states |  | Done
US-080 | E8 | Autosave and keep backups | As a player, I want the game to autosave and keep backups, so that I never lose more than a few minutes. | Scenario: Autosave Given the game is running When an in-game day ends Then it autosaves with under 200 ms of stutter Scenario: Backups Given four saves have been written When I look in the save folder Then the latest save plus 3 backups exist Scenario: Corrupt Given the latest save is corrupted When I load Then the newest valid backup loads and a message explains what happened | Must | M |  |  | M4 | US-016 | ADR-010, NFR-05 | Atomic file writes |  | Done
US-081 | E8 | Change basic settings | As a player, I want to set window mode, resolution and volume, so that the game fits my screen and ears. | Scenario: Apply Given the Settings screen When I switch to fullscreen Then the change applies immediately and is remembered next launch Scenario: Reset Given invalid values in settings.json When the game starts Then defaults are used and the file is rewritten | Should | S |  |  | M5 | US-020 | Architecture 7.8 | Reading and writing settings |  | Done
US-082 | E8 | Keep within the performance budget | As a developer, I want an FPS and tick-time overlay and a performance test, so that I notice slowdowns the day I cause them. | Scenario: Overlay Given the Debug overlay enabled When the game runs Then FPS, frame time and simulation tick time are shown Scenario: Budget Given 500 simulated agents in the region on the minimum PC When the game runs for 5 minutes Then it averages 60 FPS and ticks stay under 10 ms | Must | S |  |  | M5 | US-032, US-042, D-06 | NFR-03 | Profiling with Tracy |  | Done
US-083 | E8 | Inspect and control the world with dev tools | As a developer, I want Dear ImGui panels to inspect any person and control time, so that I can understand and tune the simulation live. | Scenario: Inspect Given the dev tools open When I click a person Then their needs, memories, relationships and AI scores are shown Scenario: Time Given the dev tools When I set speed to 16x or skip a day Then the simulation advances accordingly Scenario: Release Given a Release build When I press the dev-tools key Then nothing opens | Should | M |  |  | M4 | US-032 | ADR-015, learning stage 8 | Immediate-mode UI |  | Done
US-090 | E9 | Learn the game in the first ten minutes | As a playtester, I want a clan elder to guide me through my first day, so that I can play without reading a manual. | Scenario: Guide Given a new game with tutorial on When I start Then the elder prompts me to gather, eat, and tend the fire in order, one step at a time Scenario: Skip Given tutorial off in New Game When I start Then no prompts appear Scenario: Stuck Given I have not completed a prompt for 2 minutes When time passes Then the elder gives a hint | Should | M |  |  | M6 | US-061, D-11 | UX, NA (story) | Scripted sequences as data |  | Done
US-091 | E9 | Install and run the playtest build | As a playtester, I want a zip I can unpack and run, so that I can try the game without technical help. | Scenario: Run Given a Windows 10/11 x64 PC without developer tools When I unzip and run odysseus.exe Then the game starts with no missing-DLL errors Scenario: Crash Given a crash during play When it happens Then a crash log and the last save are written to the per-user folder for sending | Must | S |  |  | M6 | US-004, US-080 | PLT-01 | Release builds and packaging |  | Done
US-092 | E9 | Record local session statistics | As a developer, I want an opt-in local log of session length and key events, so that I can measure the MVP success criteria honestly. | Scenario: Opt-in Given first launch When the game asks about session statistics Then nothing is recorded unless I agree Scenario: Local only Given statistics enabled When a session ends Then a file with play time and key events is written locally and nothing is sent anywhere | Should | S |  |  | M6 | US-091 | MVP success criteria, ARC-04 | Privacy by design |  | Done
US-025 | E10 | Build deterministic 3D math | As a developer, I want fixed-point numbers, 3D vectors and rotations in Luna Physics, so that physics gives identical results on every computer and every run. | Scenario: Exact arithmetic Given two fixed-point values When they are added, multiplied and divided Then the results equal the expected values bit for bit in Debug, Release and CI Scenario: Rotations Given a vector rotated by 90 degrees about the up axis four times When the rotations are applied as quaternions Then it returns to the starting vector within 1/65536 of a unit Scenario: Determinism Given two runs of 1,000,000 mixed math operations with the same inputs When both finish Then both produce the same hash | Must | M |  |  | M1b | US-003 | PHY-01, ARC-10, ADR-017 | Fixed-point arithmetic; operator overloading; quaternions |  | Done
US-026 | E10 | Detect hits between shapes | As a developer, I want spheres, capsules and boxes to report overlaps, ray hits and swept hits, so that every hit is found and a fast spear never passes through its target. | Scenario: Overlap Given a sphere and a box that touch When their overlap is tested Then a hit is reported with the contact point and normal Scenario: No tunnelling Given a projectile moving 10 m per tick towards a 0.2 m target When its path is swept Then the hit is found at the correct time of impact Scenario: Many bodies Given 1,000 bodies in a region When one physics step checks them through the spatial grid Then only nearby pairs are tested and the step takes under 2 ms on the development PC | Must | L |  |  | M1b | US-025 | PHY-02, ARC-10 | Structs and pure functions; geometry; spatial grids |  | Done
US-027 | E10 | Fly projectiles with real ballistics | As a hunter, I want thrown spears and darts to fly in true arcs under gravity, drag and wind, so that aim, strength and distance matter. | Scenario: Arc Given a spear thrown at 45 degrees and 20 m/s over flat ground without drag When it lands Then its range is v^2/g = 40.8 m within 1% Scenario: Drag and wind Given the same throw with air drag and a crosswind When it lands Then it falls short and drifts downwind by the amounts the formulas predict Scenario: Aim Given a target 25 m away When the aim solver computes the launch angle for a given speed Then the thrown projectile hits the target | Must | M |  |  | M1b | US-026 | PHY-03, ADR-017 | Numerical integration; units |  | Done
US-028 | E10 | Push and bounce bodies | As a player, I want bodies to have mass, be pushed, slide, bounce and come to rest, so that knockback and thrown or falling objects feel physical. | Scenario: Impulse Given a 70 kg body at rest When an impulse of 140 N s pushes it Then its velocity becomes 2 m/s in the impulse direction Scenario: Bounce and rest Given a ball dropped onto the ground with restitution 0.5 When it bounces Then each bounce reaches a quarter of the previous height and it comes to rest Scenario: Friction Given a crate sliding on grass When no force pushes it any more Then it stops within the distance friction predicts | Must | M |  |  | M1b | US-026 | PHY-04, ADR-017 | Classes with invariants; fixed-timestep integration |  | Done
US-029 | E10 | Throw a spear in the demo | As a player, I want to throw a spear at a target in the walking skeleton, so that Luna Physics is proven end to end in the real game. | Scenario: Throw Given the hero facing a straw target 8 tiles away When I press Interact Then a spear flies in a visible arc with a shadow and hits the target Scenario: Material Given a flint-tipped and a wooden spear (materials.json) When each hits the target Then the damage differs by the materials' hardness and density as configured Scenario: Blocked Given a target behind a rock When I throw at it Then the spear hits the rock and stops; the target is unharmed | Must | M |  |  | M1b | US-024, US-027, US-028 | PHY-02, PHY-03, PHY-05 | Putting it together; content as data (materials.json) |  | Done
US-110 | E11 | Give every death and feud a reason | As a reader, I want every death and feud in the chronicle to say why it happened, so that events connect into a story. | Scenario: Death with a cause Given a person who starves after the food store was robbed or ran empty When the death is recorded Then the sentence names the cause and the event behind it, e.g. 'Winter, year 74: Hano died of hunger in the hard winter, after Brak stole from the store.' Scenario: Feud with a reason Given two people whose opinions fell through thefts, quarrels or blame When their feud begins Then the sentence names what turned them, e.g. 'A feud broke out between Tok and Brak over stolen meat.' Scenario: Traceable Given any death or feud in the chronicle When I inspect it in the headless runner Then it lists the earlier events that caused it | Must | M |  |  | M2b | US-014 | STO-03, NA-02 | Small structs that point to other data (event ids); enums | Kill Gate 1 pivot (owner, 2026-09-30, D-18) | Done
US-111 | E11 | Quarrel, blame and take revenge | As a player, I want people to quarrel, blame each other for losses and seek revenge, so that conflicts have causes and consequences. | Scenario: Quarrel Given two tired or hungry people who dislike each other When they meet Then they may quarrel; both remember it and think less of each other Scenario: Blame Given a person whose close kin died after a theft they know of, or on a hunt someone led When they grieve Then they blame the person linked to the cause and remember it for life Scenario: Revenge Given a feud that keeps worsening When revenge is taken Then it ends in a fight (injury or death) or the clan exiles the aggressor, and the chronicle tells which and why | Must | L |  |  | M2b | US-110 | SDC-02, GD-03 | State machines with enums; std::optional | Kill Gate 1 pivot (owner, 2026-09-30, D-18) | Done
US-112 | E11 | Share food and nurse the sick | As a player, I want people to share food in hard times and care for the sick and injured, so that kindness has weight and debts of gratitude form. | Scenario: Sickness Given a person weakened by cold, hunger or a hunting wound When sickness or injury strikes Then they are sick or injured for some days and may die of it Scenario: Nursing Given a sick person and a kind or close person nearby When they are nursed Then recovery is likelier and the patient remembers the carer with gratitude Scenario: Sharing and adoption Given a hungry child or an orphan When a relative or friend has food or room Then they share or adopt, and the one helped remembers it | Must | L |  |  | M2b | US-110 | SDC-02 | Standard algorithms: std::find_if, std::max_element, std::sort | Kill Gate 1 pivot (owner, 2026-09-30, D-18) | Done
US-113 | E11 | Court and compete for a partner | As a player, I want courtship with rivals and broken pairings, so that love brings drama as well as children. | Scenario: Courtship Given an unpaired adult who favours another When they court (gifts, time together) Then the other's opinion rises, and they pair only when both agree Scenario: Rivals Given two suitors courting the same person When one is chosen Then the rivals become jealous and may quarrel, and the one not chosen remembers it Scenario: Parting Given partners whose opinions of each other fall below the parting threshold When a day ends Then they part, and the chronicle records why | Must | M |  |  | M2b | US-111 | SDC-02 | Comparators and ranking (std::sort with a lambda) | Kill Gate 1 pivot (owner, 2026-09-30, D-18) | Done
US-114 | E11 | Teach the young and hunt together | As a player, I want masters to teach apprentices and hunters to go out in parties, so that skills pass down and hunts create heroes and cowards. | Scenario: Apprenticeship Given a skilled adult and a youth of working age When the adult takes the youth as apprentice Then the youth's skill grows faster and they grow close Scenario: Hunting party Given a mammoth sighting When a party of 3 to 5 hunters forms and hunts Then roles emerge (leader, hero, coward), the outcome depends on the party, and each member remembers what the others did Scenario: Rescue Given a hunter in danger When another hunter saves them Then the rescued owes a debt of gratitude and the chronicle tells of it | Must | L |  |  | M2b | US-111 | SDC-02 | A class that coordinates others (the hunting party) | Kill Gate 1 pivot (owner, 2026-09-30, D-18) | Done
US-115 | E11 | Tell the clan's story in episodes | As a reader, I want the chronicle to tell fewer, bigger episodes with a beginning, a turn and an end, so that I can follow the clan's story. | Scenario: Episode Given linked events (a lean autumn, thefts, blame, a feud, deaths) When the episode ends Then the chronicle writes it as one short named paragraph ('The Hard Winter of year 74') saying who, why and what came of it Scenario: Fewer, bigger Given a 100-year run When I print the story Then it tells at most 40 episodes, each naming its people and causes, followed by the births, deaths, pairings and feuds with their reasons Scenario: Both views Given the headless runner When I ask for the story or for the full chronicle Then --story prints the episodes and --chronicle still prints every event | Must | L |  |  | M2b | US-110, US-111, US-112, US-113, US-114 | STO-02, STO-03, NA-02 | Designing with data: grouping and summarising | Kill Gate 1 pivot (owner, 2026-09-30, D-18) | Done
US-120 | E12 | Real art in the game | As a player, I want the heroes, monsters and ground drawn from the new art, so that the world looks like the game I imagine. | Scenario: Atlas Given the owner's sprite sheets in assets/sprites When the cutter tool runs Then it writes clean atlases (transparent background, 32x48 characters, 32x32 tiles) from rectangles kept in JSON Scenario: Heroes and ground Given the game starts When the hero walks the test map Then the hero, the ground tiles and the enemy are drawn from the atlases Scenario: Missing art Given an atlas file that is missing or damaged When the game starts Then it names the file and falls back to programmer art | Must | L | 2 | 4 | M2c | - | D-05, D-19 | Reading binary files; structs of rectangles | Level editor (owner, 2026-09-30, D-19) | Done
US-121 | E12 | Point, click and read on screen | As a level designer, I want to point, click and read labels on screen, so that I can use editor tools. | Scenario: Pointer Given the mouse moves, clicks or scrolls When the events arrive Then the game reads a pointer (position, buttons, wheel), never raw SDL3 events Scenario: Text Given any label in printable ASCII When it is drawn Then it is readable and pixel-exact at 480x270 Scenario: Widgets Given a panel with buttons, a list and a number field When they are clicked or typed into Then the right action runs (tested headless) | Must | M | 1 | 2 | M2c | - | D-19, ARC-03 | Classes with virtual functions (widgets) | Level editor (owner, 2026-09-30, D-19) | Done
US-122 | E12 | Levels as data | As a level designer, I want levels saved as files, so that what I build stays and can be shared. | Scenario: Load Given a level file When the game starts Then the map, ground, characters and hero start come from the file Scenario: Round trip Given a level When it is saved and loaded Then it is exactly the same Scenario: Damaged Given a damaged level file When it is loaded Then the error names the file and the field, and the last good backup is used | Must | M | 1 | 2 | M2c | US-120 | D-19, ARC-08 | Reading and writing JSON with validation | Level editor (owner, 2026-09-30, D-19) | Done
US-123 | E12 | Game mode and Editor mode | As a level designer, I want to switch between playing and editing, so that I can try what I build at once. | Scenario: Switch Given the game running When I press F2 Then Editor mode is shown, the world pauses and the camera pans freely Scenario: Back to play Given the Editor with changes When I press F1 Then the game plays the edited level from the hero start Scenario: Game untouched Given Game mode When I play Then the spear and sword demos behave as before | Must | S | 0.5 | 1 | M2c | US-121, US-122 | D-19 | State machines (enum class) | Level editor (owner, 2026-09-30, D-19) | Done
US-124 | E12 | Paint ground tiles | As a level designer, I want to paint ground tiles by hand, so that I shape the world. | Scenario: Paint Given a tile chosen in the palette When I click or drag on the map Then the cells change; solid tiles block walking in Game mode Scenario: Fill Given an area When I use the rectangle or flood fill Then the whole area is painted in one step Scenario: Undo Given a series of edits When I press Ctrl+Z or Ctrl+Y Then the level steps back and forward exactly | Must | M | 1 | 2 | M2c | US-123 | D-19 | The command pattern (undo and redo) | Level editor (owner, 2026-09-30, D-19) | Done
US-125 | E12 | Place characters | As a level designer, I want to place heroes and monsters in the world, so that the game has someone to meet. | Scenario: Place Given a character chosen in the palette When I click on the map Then it appears there, facing south, with default properties Scenario: Edit Given a placed character When I select, move, turn or delete it, or change its name, HP or sword damage Then the change is shown and saved Scenario: Play Given a placed enemy When I hit it with the sword in Game mode Then it takes damage, flashes red and is defeated at 0 HP | Must | M | 1 | 2 | M2c | US-123, US-124 | D-19 | Owning objects in a std::vector; ids instead of pointers | Level editor (owner, 2026-09-30, D-19) | Done
US-126 | E12 | Level and character settings | As a level designer, I want to set the level's name, size, default ground and the hero's start, so that each level is my own. | Scenario: Settings Given a level When I change its name, size or default ground Then it is saved and reloaded; a resize keeps the painted tiles Scenario: Hero start Given the hero start marker When I move it Then Game mode starts the hero there Scenario: Guide Given the owner When he opens docs/guides/editor.md Then every control is explained in plain words | Must | S | 0.5 | 1 | M2c | US-125 | D-19 | Resizing a 2D grid stored in one vector | Level editor (owner, 2026-09-30, D-19) | Done
US-130 | E13 | Content catalogs from the new sheets | As the owner, I want my seven new sprite sheets cut into game atlases and catalogs, so that weapons, plants, animals, effects and weather can be used in the game. | Scenario: Cut Given the seven sheets and cuts.json When the atlas tool runs Then atlases and JSON catalogs exist for weapons, plants, animals, effects and weather, backgrounds removed Scenario: Review Given the owner When the owner opens the numbered contact sheets Then every item is shown with its catalog name | Must | L | 2 | 4 | M2d | US-120 | D-05, D-21, ARC-08 | Reading data tables with std::map and validating them | Content and combat (owner, 2026-09-30, D-21) | Done
US-131 | E13 | Hero HP, fighting back and death | As the player, I want enemies to strike back when I hit them, so that fighting has risk. | Scenario: Strike back Given an enemy the hero hits while standing within 1.5 m When 0.5 s pass with a warning flash Then the hero loses the enemy kind's damage Scenario: Death Given the hero or an enemy at 0 HP When it happens Then the hero respawns at the start with 100 HP; the enemy dies and is gone until the level restarts | Must | M | 1 | 2 | M2d | US-125 | D-21 | A small state machine with enum class | Content and combat (owner, 2026-09-30, D-21) | Done
US-132 | E13 | Effect player | As the player, I want hits, deaths and projectiles to show effects, so that combat reads clearly. | Scenario: One-shot Given an effect started in the world When its frames have played Then it disappears Scenario: Combat Given a sword hit, a death or an arrow in flight When it happens Then a hit spark, a smoke puff or a trail plays | Must | M | 1 | 2 | M2d | US-130 | D-21, ARC-09 | Timers and animation frames in a fixed timestep | Content and combat (owner, 2026-09-30, D-21) | Done
US-133 | E13 | Weapon classes and the starter set | As the player, I want each kind of weapon to fight differently, so that choosing a weapon matters. | Scenario: Classes Given each of the 8 classes When the hero attacks Then its own attack shape, speed and range are used from JSON Scenario: In hand Given a weapon selected When the hero walks Then the weapon icon is drawn in the hero's hand | Must | L | 2 | 4 | M2d | US-130, US-132 | D-21 | Virtual functions or std::variant for weapon classes | Content and combat (owner, 2026-09-30, D-21) | Done
US-134 | E13 | Pickups and the hotbar | As a level designer, I want to place weapons in my levels for the hero to find, so that levels have rewards. | Scenario: Pick up Given the hero walks over a pickup When it happens Then the weapon goes into the first free of 9 hotbar slots Scenario: Select Given weapons in the hotbar When I press 1-9 or Shift Then that weapon, or the next one, is held | Must | M | 1 | 2 | M2d | US-133 | D-21, ADR-010 | Upgrading a saved file format (version 1 to 2) | Content and combat (owner, 2026-09-30, D-21) | Done
US-135 | E13 | Elements | As the player, I want elemental weapons to do something special, so that they feel different. | Scenario: Over time Given a hit with a fire or poison weapon When seconds pass Then the target loses HP over time with its effect showing Scenario: Lightning Given a hit with a lightning weapon and a second enemy nearby When it happens Then the lightning jumps to that enemy | Should | S | 0.5 | 1 | M2d | US-133 | D-21 | Components: small structs attached to characters | Content and combat (owner, 2026-09-30, D-21) | Done
US-136 | E13 | Plants | As a level designer and player, I want plants in the world that block, can be looked at, chopped and eaten, so that the world feels alive. | Scenario: Chop Given the hero next to a plant When the player hits it with a weapon Then it is destroyed with a leaf burst; an edible plant heals 10 HP Scenario: Regrow Given a destroyed plant When 15 s pass Then the same plant grows back at a random free spot in the camera view | Must | L | 2 | 4 | M2d | US-130, US-132, US-134 | D-21 | Random numbers from a seeded stream; spatial queries | Content and combat (owner, 2026-09-30, D-21) | Done
US-137 | E13 | Animals in the Editor | As a level designer, I want to place animals, so that my levels have wildlife and dangers. | Scenario: Enemies Given a predator or boar When the hero hits it Then it takes damage and strikes back like a goblin Scenario: Bystanders Given a deer, cow or rabbit When the hero walks by Then it does nothing and cannot be hit | Must | S | 0.5 | 1 | M2d | US-130, US-131 | D-21 | Data-driven behaviour flags | Content and combat (owner, 2026-09-30, D-21) | Done
US-138 | E13 | Placed effects and random weather | As the owner, I want ambient effects and changing weather, so that the world has atmosphere. | Scenario: Weather Given Game mode When 60-120 s pass Then a random weather fades in over 3 s; clear sky comes about 1 in 3 Scenario: Repeatable Given the same seed When the game runs twice Then the same weathers come in the same order | Should | M | 1 | 2 | M2d | US-132 | D-21, ADR-011 | Blending two overlays with alpha | Content and combat (owner, 2026-09-30, D-21) | Done
US-139 | E13 | Mouse aiming | As the player, I want to aim my weapon with the mouse, so that I can attack exactly where I point. | Scenario: Face the cursor Given a weapon is held in Game mode When the mouse pointer moves around the hero Then the hero faces the pointer and an aim line and crosshair follow it Scenario: Swing toward the cursor Given a melee weapon is held and an enemy stands north-east When the pointer is north-east and I attack Then the swing hits it; with the pointer south-west it misses Scenario: Keys still work Given the Interact key When it is pressed without moving the pointer Then the attack goes toward the facing as before | Must | M |  |  | M2d | US-133, US-134 | D-25 | Converting between screen, world and angles with atan2 | Aiming and ballistics (owner, 2026-10-01, D-25) | Done
US-140 | E13 | Arc ballistics for shots | As the player, I want shots to fly as real arcs that land where I aim, so that aiming and distance matter. | Scenario: Lands at the cursor Given a launch speed and a pointer within range When a shot is fired Then it flies a ballistic arc and lands within half a metre of the pointer, the same way every run Scenario: Hits in its path Given an enemy in the path and another behind a rock When a low arc passes through the first one's body height Then it is hit; the rock blocks a low shot to the second, and a high arc clears the rock Scenario: Range and misses Given a pointer beyond the weapon's range When the shot is fired Then it lands at the range limit; a miss sticks in the ground briefly and is removed | Must | L |  |  | M2d | US-139 | D-25, ARC-10, ADR-017 | Fixed-point numbers versus floating point | Aiming and ballistics (owner, 2026-10-01, D-25) | Done
US-141 | E13 | Bows, crossbows, thrown weapons and staff bolts | As the player, I want several ranged weapons I can aim and shoot, so that I can defeat enemies from a distance. | Scenario: Each ranged class shoots Given a bow, a crossbow, a thrown weapon and a staff When each is fired at a goblin Then each hits with its own speed and path (arcs, and a flat bolt for the staff) Scenario: Elements on shots Given an elemental bow or staff When its shot hits a goblin Then the element's effect applies as for melee weapons Scenario: Shooting range Given the range level When I play it Then goblins in the open and behind rocks can be shot, and numbers are tuned in weapons.json | Must | M |  |  | M2d | US-140 | D-25 | Data-driven tuning: speeds and ranges in JSON, not in code | Aiming and ballistics (owner, 2026-10-01, D-25) | Done
US-150 | E14 | Interaction data and the rule language | As the owner, I want every action and interaction described in JSON files I can edit offline, with conditions and effects in plain words, so that I can change how the world works without code. | Scenario: Load Given gather.json with a range, a duration, two conditions and three effects When the game starts Then the interaction is registered and offered on edible plants Scenario: Error Given a file with an unknown effect verb on line 12 When the game starts Then the error reads 'interactions/gather.json:12: unknown effect verb "giv"' and the rest of the data loads Scenario: Guide Given every condition function and effect verb When the owner opens docs/guides/interaction-data.md Then each has a one-line meaning and an example | Must | L |  |  | M7 | US-060, D-34 | INT-01, INT-03, ADR-019 | A small expression parser (tokens, recursive descent) | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-151 | E14 | Tags and smart objects | As the owner, I want things to carry tags and states and to advertise the interactions that fit them, so that a new plant or object gets its actions just by its tags. | Scenario: Advertise Given a new plant kind tagged edible and plant When the hero right-clicks it Then Gather and Inspect are offered without any code change Scenario: State Given a bush in state picked When the hero right-clicks it Then Gather is shown disabled with 'Nothing to pick yet' Scenario: Unknown tag Given an interaction targeting a tag no catalog uses When the data loads Then a warning names the file and the tag | Must | M |  |  | M7 | US-150 | INT-01, INT-02, GD-04 | Sets of tags and matching with std::ranges | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-152 | E14 | The context menu from data | As the player, I want right-click actions to come from the data, so that the owner's changes appear in the game; nothing I could do before is lost. | Scenario: Same actions Given the M5 camp level When the hero right-clicks a person, the fire and the knapping stone Then Talk, Give berries, Ask to teach, Craft, Eat berries and Tend the fire are offered as before Scenario: Data change Given the owner renames 'Tend the fire' in tend-fire.json When the game reloads the data Then the menu shows the new name Scenario: Regression Given the M5 and M6 tests When they run Then they pass unchanged | Must | L |  |  | M7 | US-151, US-061 | INT-01, INT-03 | Replacing hard-coded behaviour behind a stable interface (refactoring with tests) | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-153 | E14 | Timed actions and world state | As the player, I want actions to take time, show progress and change the thing I act on, so that the world reacts and remembers. | Scenario: Progress Given Gather with a duration of 3 s When the hero starts it Then a progress ring fills over 3 s and the berries arrive at the end Scenario: Interrupt Given a timed action under way When the player moves or attacks Then the action stops and gives nothing Scenario: Saved Given a bush picked and a fire lit When the game saves and loads Then the bush is still picked and the fire still burns | Must | M |  |  | M7 | US-152 | INT-04 | Timers in the fixed timestep; saving component state | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-154 | E14 | NPCs and animals use interactions | As the player, I want clan members and animals to do the same things I can do, chosen by their needs and traits, so that I see them live in the world. | Scenario: Hungry Given a hungry clan member near a ripe bush When time passes Then they walk to the bush and gather, and the bush shows as picked Scenario: Animals Given a deer near grass and a wolf nearby When time passes Then the deer grazes and flees from the wolf Scenario: Deterministic Given the same seed and inputs When two runs simulate 10,000 ticks Then the world hashes match | Must | L |  |  | M7 | US-153, US-030 | INT-05, SDC-02 | Utility scoring; sharing one system between player and AI | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-155 | E14 | Age 1 world objects | As a level designer, I want fire pits, knapping stones, stores, shelters, flint nodules, water and sleeping furs as placeable objects with their own actions, so that a camp is something to interact with. | Scenario: Place Given the Editor's object palette When the owner places a fire pit Then it appears in the level and is saved Scenario: Use Given a fire pit with no fire When the hero chooses Light fire with a fire drill Then the fire burns and warms people nearby Scenario: Data Given a new object kind added to objects.json When the game reloads Then it appears in the palette with its tags | Should | M |  |  | M7 | US-151 | INT-02, INT-04 | Data-driven object kinds | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-156 | E14 | Hot reload and the validation panel | As the owner, I want to press F5 after editing a file offline and see my change, or a clear list of mistakes, so that I can iterate fast without restarting. | Scenario: Reload Given the game running and gather.json edited in Notepad When the owner presses F5 Then the change is live within a second Scenario: Bad file Given a file with a syntax error When the owner presses F5 Then a panel lists 'file:line: message' and the last good data stays in use Scenario: Fix Given the panel showing an error When the owner fixes the file and presses F5 Then the panel closes and the new data is used | Must | M |  |  | M7 | US-150 | INT-03 | Watching files and swapping data safely | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-160 | E15 | The dialogue script format | As the owner, I want to write conversations as plain text with speakers, choices, conditions and effects, so that I can write dialogue in any text editor. | Scenario: Parse Given elder-fire.dlg with three nodes, a conditional line and three choices When the game loads it Then the conversation has three nodes and the choices link to them Scenario: Error Given a choice that points to a missing node on line 9 When the game loads it Then the error reads 'dialogue/elder-fire.dlg:9: unknown node "hunts"' Scenario: Round trip Given every shipped .dlg file When it is loaded and written back Then the text is the same, # notes included | Must | L |  |  | M8 | US-150 | SDC-03, SDC-04, ADR-019 | Writing a line-based parser and a printer that round-trip | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-161 | E15 | Conversations and the dialogue panel | As the player, I want to talk to an NPC in a panel with their name, mood, words and my choices, so that speaking to people is part of play. | Scenario: Talk Given the hero next to the elder When the player chooses Talk Then the game pauses and the panel shows the elder's name, mood, first line and numbered choices Scenario: Choose Given the choice 'Offer berries' with its effects When the player picks it with the mouse or the key 2 Then a berry leaves the bag, the elder's opinion rises by 5 and the next node is shown Scenario: Hidden Given a choice whose condition is false When the node is shown Then the choice is hidden, or shown disabled when the script marks it so | Must | L |  |  | M8 | US-160 | SDC-03 | A small state machine over data; immediate-mode UI | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-162 | E15 | Who says what | As the owner, I want conversations chosen by character, role, kind, opinion and priority, with short greetings, so that each NPC sounds like themselves. | Scenario: Specific first Given a script for the placed character 'Ama' and one for all elders When the hero talks to Ama Then Ama's own script is used Scenario: Opinion Given a script with @when opinion(npc, hero) < -30 When an NPC who dislikes the hero is spoken to Then that script is used Scenario: Greeting Given the hero passing within 3 m of a friendly NPC When it happens Then a short greeting bubble appears, at most once a minute per NPC | Must | M |  |  | M8 | US-161 | SDC-03 | Ranking candidates with std::ranges::max_element | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-163 | E15 | Generated small talk | As the player, I want NPCs without a written line to talk about what they remember, what they heard and how they feel, so that every clan member has something to say. | Scenario: Memory Given an NPC who saw a wolf at the fire yesterday When the hero talks to them with no script Then they mention the wolf in their own words Scenario: Gossip Given an NPC who heard that Bo blamed Ama When the topic 'people' comes up Then they repeat the gossip and say how they feel about it Scenario: Variety Given 50 small-talk lines from one seed When the owner reads them Then no line repeats more than twice | Must | M |  |  | M8 | US-161, US-012 | SDC-03, STO-02 | Text templates with tokens | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-164 | E15 | Conversations are remembered | As the player, I want what I say to matter later, so that people remember kindness and insults and talk about them. | Scenario: Memory Given the hero insults Bo in a conversation When it ends Then Bo has a memory with a bad feeling and his opinion of the hero falls Scenario: Gossip Given that memory When two days pass Then Bo's friends have heard it at half strength Scenario: Saved Given flags set in conversations When the game saves and loads Then the flags and the conversation memories are still there | Must | M |  |  | M8 | US-161 | SDC-03, SDC-02, STO-03 | Linking dialogue effects to the memory system | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-165 | E15 | NPCs talk to each other | As the player, I want to see clan members talk in speech bubbles, so that quarrels, courtship and sharing happen in front of me. | Scenario: Bubbles Given two friends at the fire in the evening When they talk Then bubbles with short lines appear over their heads in turn Scenario: Quarrel Given a quarrel started by the social simulation When it happens near the hero Then the quarrel is shown as angry lines and both opinions fall Scenario: Readable Given a bubble on screen When 3 s pass or the next line starts Then it disappears | Should | M |  |  | M8 | US-162, US-154 | SDC-05, SDC-02 | Scheduling short timed events | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-170 | E16 | Node-graph widget | As the owner, I want a canvas with nodes and wires that I can pan, zoom, select, drag and undo, so that rules and conversations can be edited visually. | Scenario: Edit Given an empty graph When the owner adds two nodes and drags a wire between their ports Then the wire connects them Scenario: Navigate Given a graph larger than the screen When the owner drags with the right button and turns the wheel Then the view pans and zooms around the cursor Scenario: Undo Given ten graph edits When the owner presses Ctrl+Z ten times Then the graph is as it was | Must | L |  |  | M9 | US-121, US-126 | INT-06, SDC-06, ARC-09 | Graph data structures; hit testing; the Command pattern | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-171 | E16 | Dialogue graph editor | As the owner, I want to open a conversation as a graph, edit lines, choices, conditions and effects, and save it, so that I can write dialogue in the game. | Scenario: Open Given elder-fire.dlg When the owner opens it in the Editor Then each node is a box with its lines and each choice is a wire to its target Scenario: Save Given a node added and a choice rewired When the owner presses Ctrl+S Then the .dlg text shows the change in canonical form and the positions are in elder-fire.dlg.layout.json Scenario: Hand edits Given a file edited in Notepad with # notes When it is opened, changed in the graph and saved Then the notes are still there | Must | L |  |  | M9 | US-170, US-160 | SDC-06, INT-03 | Mapping between a text format and a graph | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-172 | E16 | Interaction graph editor | As the owner, I want to see and edit interactions as actor, verb and target nodes with condition and effect blocks, so that I can design how things act on each other. | Scenario: View Given the interactions folder When the owner opens the interaction graph Then actors, verbs and target tags are nodes and each interaction is a path between them Scenario: Edit Given Gather selected When the owner changes its duration to 2 s and adds the effect 'fx leaves' Then gather.json is saved with the change Scenario: Pickers Given a condition or effect field When the owner types Then items, tags, needs and nodes are offered from the catalogs | Must | L |  |  | M9 | US-170, US-150 | INT-06 | Forms built from a schema; pickers over catalogs | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-173 | E16 | Attach to placed things | As a level designer, I want to give a placed character a conversation and a placed object its own interactions, so that each level can have its own people and places. | Scenario: Attach Given a placed character selected When the owner picks 'elder-fire' as its dialogue Then talking to that character in Game mode starts elder-fire Scenario: Override Given a placed bush selected When the owner sets its regrow time to 60 s Then only that bush regrows in 60 s Scenario: Saved Given attached dialogues and overrides When the level is saved and loaded Then they are still attached | Must | M |  |  | M9 | US-171, US-172 | SDC-06, INT-06 | Per-instance overrides of shared data | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-174 | E16 | Test-play from the Editor | As the owner, I want to play a conversation or an interaction from the Editor with conditions I choose, so that I can check every branch without playing the game for hours. | Scenario: Branch Given a choice that needs opinion >= 20 When the owner sets the opinion to 25 and test-plays Then the choice is offered Scenario: Start anywhere Given a node selected When the owner chooses Play from here Then the conversation starts at that node Scenario: No side effects Given a test-play that gives items When it ends Then the level and the save are unchanged | Should | M |  |  | M9 | US-171, US-172 | SDC-06, INT-06 | Faking inputs for tests (test doubles) | World interactions and dialogue (owner, 2026-10-01, D-34) | To do
US-175 | E16 | Graph validation | As the owner, I want unreachable nodes, dead ends and unknown names listed and clickable, so that broken conversations never reach players. | Scenario: Unreachable Given a node no choice leads to When validation runs Then it is listed and clicking it selects the node Scenario: Dead end Given a node with no choice and no END When validation runs Then it is listed as a dead end Scenario: Unknown Given an effect giving an item no catalog has When validation runs Then the item name and the node are listed | Must | S |  |  | M9 | US-171, US-172 | INT-03, SDC-06 | Graph traversal (breadth-first search) | World interactions and dialogue (owner, 2026-10-01, D-34) | To do

## Cut List
Out of the MVP (and when it returns)
Saying no, with reasons. Nothing here is lost: each item returns on the roadmap.
Item | Why it is cut from the MVP | Returns
Android and iOS builds | No hypothesis depends on them; architecture already protects portability. | After MVP (learning stage 11)
Ages 2-10, Mythic Strands, Phase 2 space | Each is a content project; the MVP must first prove Age 1 is fun. | Post-MVP roadmap
Whole planet, prehistory world-gen, LOD tiers Remote and Planet | A region is enough to test the loop; planet scale is a performance project of its own. | Next
Military, Politics, Technology, Ideology pillars | Two pillars are enough to test 'many paths to dominance'; combat is the most expensive system. | Next (Politics), Later (others)
Dynasty, Reincarnation, Rotating Avatar modes | One mode tests the loop; the Succession system is built so others are configuration later. | Next (Dynasty)
Character Creator, Origin/Tribe, Legend modifiers | Unlocks need progression that the MVP does not have yet. | Next
Ideology Forge, custom titles | Depend on cut pillars. | Later
Real art pipeline, music | Placeholder art is enough to test fun; art is expensive to redo. | After the fun is proven
Steam integration, achievements, cloud saves | Distribution is not the MVP question (OPEN-18). | Launch
Advanced physics and chemistry (explosions, vehicles, orbits, heat, fire spread, reactions) | Age 1 needs hit detection, ballistics, basic bodies and material properties only; the rest belongs to later Ages. | With the Age that needs it (PHY-05, PHY-06)

## Ready & Done
Definition of Ready and Definition of Done
Apply to every story.
Definition of Ready: a story may start when...
The story traces to an MVP scope item or a requirement.
Its design dependencies are Decided (see Dependencies).
Acceptance criteria are testable and agreed.
It fits in one milestone; if larger than L, it is split first.
Definition of Done: a story is Done when...
Code compiles with zero warnings in Debug and Release (x64).
All acceptance criteria verified; automated tests written where the story is testable headless.
CI is green on the main branch.
No layer rule broken (Simulation does not include Engine, Platform or SDL3).
Determinism test still passes.
Code reviewed with Dominus; anything unclear explained in the learning journal.
Requirements document updated if behaviour differs from what it says.